## PO Tracker
PURCHASE ORDER TRACKER — ADI PROCUREMENT PROJECT
Sreya Ghosh · Procurement Operations Practice Model · 2026
PO Number | Vendor Name | Item Description | Category | Qty Ordered | Unit Price (₹) | Total Value (₹) | Order Date | Expected Delivery | Actual Delivery | Status | Days Overdue | Remarks
PO-10001 | Murata Electronics | Capacitor 100nF SMD | Components | 5000 | 18.5 | 92500 | 24-Feb-2026 | 21-Mar-2026 | 20-Mar-2026 | Delivered | 0 | Delivered on time
PO-10002 | Texas Instruments | IC Op-Amp TL072 | ICs | 2000 | 85 | 170000 | 26-Feb-2026 | 23-Mar-2026 | 22-Mar-2026 | Delivered | 0 | Early delivery
PO-10003 | Vishay Components | Resistor 10K 0603 | Components | 10000 | 2.2 | 22000 | 01-Mar-2026 | 28-Mar-2026 |  | Open | 0 | On track
PO-10004 | Molex Connectors | JST 2-pin Connector | Connectors | 3000 | 12.75 | 38250 | 04-Mar-2026 | 25-Mar-2026 |  | Backorder | 1 | Supplier short by 1200 units — escalated
PO-10005 | Samsung Semicon | NAND Flash 4GB | Memory | 500 | 420 | 210000 | 06-Mar-2026 | 27-Mar-2026 |  | Acknowledged | 0 | Confirmed by supplier 20-Mar
PO-10006 | Infineon Tech | IGBT Module 600V | Power | 200 | 1850 | 370000 | 08-Mar-2026 | 22-Mar-2026 |  | Open | 4 | Overdue — follow up initiated
PO-10007 | Amphenol Corp | RF Coaxial Cable 1m | Cables | 1500 | 95 | 142500 | 11-Mar-2026 | 29-Mar-2026 |  | Acknowledged | 0 | Supplier ack 22-Mar, on schedule
PO-10008 | Bourns Inc | Inductor 100uH | Components | 8000 | 7.8 | 62400 | 14-Mar-2026 | 24-Mar-2026 |  | Backorder | 2 | Vendor capacity issue — alt sourcing in progress
PO-10009 | TE Connectivity | Terminal Block 4-way | Connectors | 2500 | 28.5 | 71250 | 16-Mar-2026 | 31-Mar-2026 |  | Open | 0 | Within lead time
PO-10010 | STMicroelectronics | MCU STM32F103 | ICs | 800 | 285 | 228000 | 18-Mar-2026 | 23-Mar-2026 |  | Open | 3 | Overdue — escalated to category manager
PO-10011 | Panasonic Corp | Electrolytic Cap 470uF | Components | 4000 | 14.2 | 56800 | 20-Mar-2026 | 30-Mar-2026 |  | Open | 0 | On track
PO-10012 | NXP Semiconductors | CAN Bus Transceiver | ICs | 1200 | 165 | 198000 | 21-Mar-2026 | 28-Mar-2026 |  | Acknowledged | 0 | PO acknowledged, delivery confirmed
PO-10013 | Wuerth Elektronik | EMI Filter SMD | Components | 6000 | 9.5 | 57000 | 23-Mar-2026 | 02-Apr-2026 |  | Open | 0 | New vendor — monitoring closely
PO-10014 | Kemet Electronics | Film Capacitor 1uF | Components | 3500 | 22 | 77000 | 24-Mar-2026 | 05-Apr-2026 |  | Open | 0 | Adequate lead time
PO-10015 | Littelfuse Inc | Fuse 2A 250V | Protection | 5000 | 8.9 | 44500 | 25-Mar-2026 | 07-Apr-2026 |  | Open | 0 | Standard order
LEGEND: |  | Delivered |  | Acknowledged |  | Open |  | Backorder / Overdue
Formulas:
Days Overdue = IF([Status]="Delivered",0,IF(AND([Status]<>"Delivered",ISNUMBER(DATEVALUE([Expected Delivery]))),MAX(0,TODAY()-DATEVALUE([Expected Delivery])),0))

## Dashboard
PROCUREMENT DASHBOARD — SUMMARY & KPIs
As of: 26 March 2026 · Auto-calculated from PO Tracker sheet
| Total POs |  | Total Spend (₹) |  | Overdue POs |  | Backorders
| 15 |  | 1840200 |  | 4 |  | 2
| Delivered |  | Acknowledged |  | Open Orders |  | Avg Order Value
| 2 |  | 3 |  | 8 |  | 122680
| STATUS BREAKDOWN |  |  |  |  | OVERDUE / BACKORDER ALERTS
| Status | Count | Total Value (₹) | % of Spend |  | PO Number | Vendor | Status | Days Late
| Delivered | 2 | 262500 | 14.26% |  | PO-10004 | Molex Connectors | Backorder | 1
| Open | 8 | 926550 | 50.35% |  | PO-10006 | Infineon Tech | Open | 4
| Acknowledged | 3 | 550500 | 29.92% |  | PO-10008 | Bourns Inc | Backorder | 2
| Backorder | 2 | 100650 | 5.47% |  | PO-10010 | STMicroelectronics | Open | 3
| TOTAL | 15 | 1840200 | 100%
| SPEND BY CATEGORY |  |  |  |  | HOW TO USE THIS TRACKER
| Category | PO Count | Total Spend (₹) | % of Total |  | 1. | Go to 'PO Tracker' tab to view / add purchase orders
| Cables | 1 | 142500 | 7.744% |  | 2. | Enter PO details — status updates drive dashboard automatically
| Components | 6 | 367700 | 19.98% |  | 3. | Red rows = Backorder or Overdue — requires immediate buyer action
| Connectors | 2 | 109500 | 5.95% |  | 4. | Green rows = Delivered — 3-way match can be initiated
| ICs | 3 | 596000 | 32.39% |  | 5. | Blue rows = Acknowledged — monitor for delivery
| Memory | 1 | 210000 | 11.41% |  | 6. | Days Overdue column auto-calculates from today's date
| Power | 1 | 370000 | 20.11% |  | 7. | Dashboard KPIs refresh automatically as data changes
| Protection | 1 | 44500 | 2.418% |  | 8. | In SAP: ME21N=Create PO · MIGO=Goods Receipt · ME2M=Open POs
| TOTAL | 15 | 1840200 | 100.0%

## Vendor Master
VENDOR MASTER LIST — APPROVED SUPPLIERS
Vendor ID | Vendor Name | Category | Country | Lead Time (days) | Payment Terms | Status
V-001 | Murata Electronics | Components | Japan | 14 | Net 30 | Active
V-002 | Texas Instruments | ICs | USA | 21 | Net 45 | Active
V-003 | Vishay Components | Components | USA | 10 | Net 30 | Active
V-004 | Molex Connectors | Connectors | USA | 18 | Net 30 | Active
V-005 | Samsung Semicon | Memory | South Korea | 25 | Net 60 | Active
V-006 | Infineon Tech | Power | Germany | 20 | Net 45 | Active
V-007 | Amphenol Corp | Cables | USA | 12 | Net 30 | Active
V-008 | Bourns Inc | Components | USA | 15 | Net 30 | On Hold
V-009 | TE Connectivity | Connectors | Switzerland | 17 | Net 30 | Active
V-010 | STMicroelectronics | ICs | Switzerland | 22 | Net 45 | Active
V-011 | Panasonic Corp | Components | Japan | 14 | Net 30 | Active
V-012 | NXP Semiconductors | ICs | Netherlands | 19 | Net 45 | Active
V-013 | Wuerth Elektronik | Components | Germany | 16 | Net 30 | Active
V-014 | Kemet Electronics | Components | USA | 13 | Net 30 | Active
V-015 | Littelfuse Inc | Protection | USA | 11 | Net 30 | Active
Active Vendors: | 14